CARE Honduras

Youth Employability and Climate Resilience Project (P176724)

Final

# ENVIRONMENTAL and SOCIAL COMMITMENT PLAN (ESCP)

# June 5, 2024

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- CARE Honduras (the Recipient) will be implementing the “Youth Employability and Climate Resilience Project” (P176724) (the Project), as established in the Grant Agreement. The International Development Association (hereinafter the Bank) acting as the administrator of the Japanese Social Development Fund (JSDF) has agreed to provide financing for the Project.

- The Recipient shall ensure that the Project is carried out in accordance with the Environmental and Social Standards (ESSs) and this ESCP, in a manner acceptable to the Bank. The ESCP is part of the Grant Agreement. Unless otherwise defined in this ESCP, capitalized terms used in this ESCP have the meanings ascribed to them in the referred agreement.

- Without limitation to the foregoing, this ESCP sets out material measures and actions that the Recipient shall carry out or cause to be carried out, including, as applicable, the timeframes of the actions and measures, institutional, staffing, training, monitoring, and reporting arrangements, and grievance management. The ESCP also sets out the environmental and social (E&S) instruments that shall be adopted under the Project, all of which shall be subject to prior consultation and disclosure, consistent with the ESS, and in form and substance, and in a manner acceptable to the Bank. Once adopted, said E&S instruments may be revised from time to time with prior written agreement by the Bank.

- As agreed by the Bank and the Recipient, this ESCP will be revised from time to time if necessary, during the implementation of the Project, to reflect adaptive management of Project changes and unforeseen circumstances related to the Project or in response to assessment of performance of the Project. In such circumstances, the Recipient and the Bank agree to update the ESCP to reflect such amendments through an exchange of signed correspondence between the Bank and the Director of CARE-Honduras or his delegate.  the Recipient shall promptly disclose the updated ESCP.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBLE ENTITY |
| --- | --- | --- | --- |
| MONITORING AND REPORTING |  |  |  |
| A | REGULAR REPORTING Prepare and submit regular monitoring reports on the environmental, social, health, and safety (ESHS) performance of the Project, including but not limited to the implementation of this ESCP, status of preparation and implementation of E&S instruments required under the ESCP, stakeholder engagement activities, and functioning of the grievance mechanisms. | Submit bi-annual reports during Project implementation, starting from the Effective Date and no later than forty-five (45) days following the end of each semester. | CARE Honduras |
| B | INCIDENTS Y ACCIDENTS Promptly notify the Bank of any incident or accident related or having an impact on the Project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers including, inter alia, cases of sexual exploitation and abuse (SEA), sexual harassment (SH), and accidents that result in death, serious or multiple injury. Provide sufficient detail regarding the incident or accident, indicating immediate measures taken to address it, and include information provided by any contractor and supervising entity, as appropriate. Subsequently, as per the Bank’s request, prepare a report on the incident or accident and propose any measures to prevent its recurrence. The guideline “Responses to Environmental, Social, and Occupational Health and Safety Incidents for Projects Financed by the World Bank (WB)”, shall be included as an annex to the Project Operational Manual (POM). | Notify the Bank no later than twenty-four (24) hours after taking notice of the incident or accident. Any subsequent report would be provided within a timeframe acceptable to the Bank. | CARE Honduras |
| C | CONTRACTORS’ MONTHLY REPORTS Require contractors and supervising firms to provide monthly monitoring reports on ESHS performance in accordance with the metrics specified in the respective bidding documents and contracts and submit such reports to the Bank. | Submit the monthly reports to the Bank as annexes to the reports to be submitted under Action A above. | CARE Honduras |
| EAS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ORGANIZATIONAL STRUCTURE The Recipient shall establish and maintain a Project Implementation Unit (PIU), with an organizational structure, qualified staff and resources to support, among others, the management of E&S risks and impacts, including the following key personnel: - One (1) Environmental & Social Specialist. The E&S Specialist shall have qualifications and experience acceptable to the Bank. In addition, they must sign the Project's code of conduct. | E&S Specialist to be hired or appointed no later than thirty (30) days after the Effective Date and shall be maintained throughout Project implementation. | CARE Honduras |
| 1.2 | MANAGEMENT TOOLS AND INSTRUMENTS - An initial draft Environmental and Social Management Framework (ESMF) has been prepared and disclosed for the Project. This draft shall be updated, finalized and redisclosed to include, among others, a Project-level Environmental and Social Management Plan (ESMP), and on an ongoing basis as required based on experience implementing the Project. - Implement the Project in accordance with the ESMF. This includes screening, assessing, managing, and monitoring any proposed activity in accordance with the ESMF. Any proposed activity that falls within the exclusion criteria of the ESMF shall not be eligible for financing. - Site-specific ESMPs shall be developed for works under Component 2 in accordance with the Project-level ESMP included in the ESMF. The site-specific ESMPs shall be included in the bidding documents to serve as a base model for contractors to prepare a Contractor’s ESMP (C-ESMP) for each of the civil works. The C-ESMPs shall include mitigation measures with more specificity as applicable depending on the specific works to be carried out and the conditions of the site. | - Initial draft ESMF to be updated, finalized and redisclosed within sixty (60) days of the Effective Date and prior to beginning implementation of Project activities. - The ESMF shall be implemented throughout Project implementation. - Site-specific ESMPs for works to be prepared and submitted to the Bank for approval prior to bidding the respective works. | CARE Honduras |
| 1.3 | MANAGEMENT OF CONTRACTORS Incorporate the relevant aspects of the ESCP, including, inter alia, the relevant E&S instruments, the Labor Management Procedures, and code of conduct, into the ESHS specifications of the procurement documents and contracts with contractors and supervising firms. Thereafter ensure that the contractors and supervising firms comply and cause subcontractors to comply with the ESHS specifications of their respective contracts. | As part of the preparation of procurement documents and respective contracts. Supervise contractors throughout Project implementation | CARE Honduras |
| 1.4 | PERMITS, CONSENTS AND AUTHORIZATIONS Obtain or assist in obtaining, as appropriate, the permits, consents and authorizations that are applicable to the Project from relevant national authorities. Comply or cause to comply, as appropriate, with the conditions established in these permits, consents, and authorizations throughout Project implementation. | As applicable, to be obtained prior to initiating activities that require permits, consents, and authorizations. | CARE Honduras |
| EAS 2: LABOR AND WORKING CONDITIONS |  |  |  |
| 2.1 | LABOR MANAGEMENT PROCEDURES (LMP) Develop, adopt, disclose and implement Labor Management Procedures (LMP) for the Project, including, inter alia, provisions on working conditions, management of workers relationships, occupational health and safety (including personal protective equipment, and emergency preparedness and response), code of conduct (including relating to SEA and SH), forced labor, child labor, grievance arrangements for Project workers, and applicable requirements for contractors, subcontractors, and supervising firms. LMP will include occupational, health and safety (OHS) measures, including, inter alia, emergency preparedness and response measures, and measures to ensure the use of appropriate personal safety equipment for all workers, including community workers and youth trainees, according to the activity carried out and in accordance with current national labor regulations. | Develop, adopt and disclose within sixty (60) days of the Effective Date and prior to beginning implementation of Project activities, and thereafter implement the LMP throughout Project implementation. | CARE Honduras |
| 2.2 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Develop, maintain, and operate a grievance mechanism for Project workers as described in the LMP. | Same timeline as action 2.1 above and maintained throughout Project implementation. | CARE Honduras |
| EAS 3: RESOURCE USAGE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |
| 3.1 | MANAGEMENT OF WASTE AND HAZARDOUS MATERIALS Ensure the least possible use of hazardous substances for any proposed subproject and activity, promoting their substitution by less polluting products more friendly to the environment, in accordance with the ESMF. | Any relevant site-specific measures for waste and hazardous management to be identified during works screening and assessment and reflected in bid/contract/works documents prior to initiating activities for corresponding works, in accordance with the ESMF and ESMPs. All measures implemented and monitored as applicable throughout Project implementation. | CARE Honduras |
| 3.2 | LAND, WATER AND OTHER RESOURCES MANAGEMENT As part of planning and implementation for all works, the following objectives shall be pursued, as set out in the ESMF: - Promote the rational and appropriate use of land / geographical space to be developed in small works (strictly necessary area of land is used for this purpose). - Promote the application of direct measures and actions for the rational/ efficient use of water and energy in all stages and activities. These measures shall be reflected within infrastructure plans and designs, wherever technically and financially feasible. - Include specific constructive and operational actions that avoid the inappropriate and irrational use of all resources. | Site-specific measures identified during works screening, ESMPs and reflected in bid/ contract/ works documents. | CARE Honduras |
| EAS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |
| 4.1 | TRAFFIC AND ROAD SAFETY Incorporate measures to manage traffic and road safety risks as required in the ESMPs to be prepared under action 1.2 above. | Same timeframe as for the adoption and implementation of the ESMPs. | CARE Honduras |
| 4.2 | COMMUNITY HEALTH AND SAFETY Assess and manage specific risks and impacts to the community arising from Project activities, including minor impacts as a result of civil works, behavior of Project workers, risks of labor influx, response to emergency situations, and include mitigation measures in the ESMPs to be prepared in accordance with the ESMF. | Same timeframe as for the adoption and implementation of the ESMPs. | CARE Honduras |
| 4.2 | SEA AND SH RISKS Adopt and implement a SEA/SH prevention measures as part of the ESMPs to assess and manage the risks of SEA and SH. | Same timeframe as for the adoption and implementation of the ESMPs. | CARE Honduras |
| EAS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT |  |  |  |
| This standard is not relevant. |  |  |  |
| EAS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES |  |  |  |
| This standard is not relevant. |  |  |  |
| EAS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES |  |  |  |
| This standard is not relevant. |  |  |  |
| EAS 8: CULTURAL HERITAGE |  |  |  |
| 8.1 | CHANCE FINDS Describe and implement the chance finds procedures, as part of the ESMPs of the Project. | Describe the chance find procedures in the ESMPs. Implement the procedures throughout Project implementation. | CARE Honduras |
| EAS 9: FINANCIAL INTERMEDIARIES |  |  |  |
| This standard is not relevant. |  |  |  |
| EAS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN An initial Stakeholder Engagement Plan (SEP) for the Project, consistent with ESS10, has been drafted, consulted and disclosed during Project preparation. The SEP shall include measures to, inter alia, provide stakeholders with timely, relevant, understandable and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation. The SEP shall be updated and redisclosed after effectiveness. | Initial draft SEP to be updated, finalized and redisclosed within sixty (60) days of the Effective Date and prior to beginning implementation of Project activities and thereafter implement the SEP throughout Project implementation. | CARE Honduras |
| 10.2 | PROJECT GRIEVANCE MECHANISM Establish, publicize, maintain, and operate an accessible grievance mechanism, to receive and facilitate resolution of concerns and grievances in relation to the Project, promptly and effectively, in a transparent manner that is culturally appropriate and readily accessible to all Project-affected parties, at no cost and without retribution, including concerns and grievances filed anonymously, in a manner consistent with ESS10. The grievance mechanism shall be equipped to receive, register, and facilitate the resolution of SEA/SH complaints, including through the referral of survivors to relevant gender-based violence (GBV) service providers, all in a safe, confidential, and survivor-centered manner. | Establish the grievance mechanism within sixty (60) days of Project effectiveness and prior to beginning implementation of Project activities, and thereafter maintain and operate the mechanism throughout Project implementation. | CARE Honduras |
| CAPACITY SUPPORT (TRAINING) |  |  |  |
| C | - Provide specific training to project workers, contractors, community-based organizations, and other project beneficiaries, as relevant, on: - E&S risks and impacts. - Implementation of E&S instruments developed and disclosed for the Project. - Participatory monitoring and evaluation of E&S requirements. - Report on the training provided. | - Training to Project workers and contractors will be conducted by the Project E&S Specialist for the duration of the Project and start within the first three (3) months of Project effectiveness. Training to community-based organizations will be conducted after subprojects approved, within the first six (6) months of Project effectiveness. - As a part of the bi-annual reports submitted to the Bank as required by Action A. | CARE Honduras |